## Task List
Task ID | Task Name | Team | Deadline
PM01 | Discuss with client about the look, theme and expectation | Product Managment | 1 day
PM02 | Presentation of themes | Product Managment | 1 day
PM03 | Wireframing with theme presentation and taking feedback from team | Product Managment | 1 day
PM04 | Sprint Meeting | Product Managment | 1 day
PM05 | Discuss with client about the look, theme and expectation | Product Managment | 1 day
PM06 | Feedback and changes after client meeting (Day 1) | Product Managment | 1 day
PM07 | Feedback and changes after client meeting (Day 2) | Product Managment | 1 day
7 days
D01 | Reference and Samples | Design | 1 day
D02 | Website Wireframing | Design | 3 days
D03 | Prototyping of website with selected theme after wireframing | Design | 4 days
D04 | Feedback of the prototype from the customer | Design | 1 day
D05 | Logo sketching | Design | 1 day
D06 | Logo 1st Digital drawing | Design | 1 day
D07 | Logo 2nd digital drawing | Design | 1 day
D08 | Logo final drawing | Design | 3 days
D09 | Applying Final changes and handing over logo to development team | Design | 1 day
16 days
DEV01 | Home/Index page development | Web Development | 1 day | design team
DEV02 | Book free consultation form development for home page | Web Development | 2 days
DEV03 | Package and plan page | Web Development | 2 days
DEV04 | Body Type & Health / Diet Guide page | Web Development | 2 days
DEV05 | Blogs page development | Web Development | 2 days
DEV06 | Our Partners page development | Web Development | 2 days
DEV07 | Diet Survey Page development | Web Development | 2 days
DEV08 | FAQ Page | Web Development | 2 days
DEV09 | Implementing changes from sprint 2 testing and feedback from client | Web Development | 1 day
DEV10 | Implementing logo on website | Web Development | 1 day
DEV11 | Customer feedback implementation until sprint 2 on sites | Web Development | 1 day
DEV12 | Admin Portal development | Web Development | 5 days
DEV13 | Implementing changes from sprint 3 testing | Web Development | 1 day
DEV14 | Customer feedback implementation until sprint 3 on sites | Web Development | 1 day
DEV15 | Webhosting and database setup, live website | Web Development | 1 day
DEV16 | Implementing changes and fixing bugs from full testing | Web Development | 1 day
DEV17 | Making changes on customer feedback | Web Development | 1 day
DEV18 | Website Live Monitoring | Web Development | 1 day
29 days
QA1 | Testing for products created on first 2 sprint | Testing | 3 days
QA2 | Testing review for sprint 2 submission | Testing | 1 day
QA3 | Testing for products created on first 3 sprints | Testing | 2 days
QA4 | Testing review for sprint 3 submission | Testing | 1 day
QA5 | Full website testing | Testing | 2 days
QA6 | Testing review for full testing | Testing | 1 day
10 days

## Timeline
Sprint | Week | Date | Day | PM Task | Designer task | Developer Task | Tester Task
Sprint 1 | 1 | 2022-11-14 | Monday | Discuss with client about the theme and the look of the website
| 1 | 2022-11-15 | Tuesday |  | Reference and Samples
| 1 | 2022-11-16 | Wednesday | Presentation of sample themes | Website wireframe Design
| 1 | 2022-11-17 | Thursday | Team Meeting | Team Meeting | Team Meeting | Team Meeting
| 1 | 2022-11-18 | Friday | Team Meeting | Team Meeting | Team Meeting | Team Meeting
|  | 2022-11-19 | Saturday
|  | 2022-11-20 | Sunday
| 2 | 2022-11-21 | Monday | Sprint Meeting for 1st sprint | Prototyping of website with selected themes
| 2 | 2022-11-22 | Tuesday | Wireframing and prototyping
| 2 | 2022-11-23 | Wednesday | Presentation and feedback from customer
| 2 | 2022-11-24 | Thursday |  | Impementing feedback from customer on mockup creating prototype
| 2 | 2022-11-25 | Friday | Team Meeting | Team Meeting | Home/Index page prototype creation & Team Meeting | Team Meeting
|  | 2022-11-26 | Saturday
|  | 2022-11-27 | Sunday
Sprint 2 | 3 | 2022-11-28 | Monday | Sprint Meeting for 2nd sprint | Logo concept sketch | Book free consultation from creation for home page DAY 1
| 3 | 2022-11-29 | Tuesday | Discuss with client & brainstorm about concept |  | '' " DAY 2
| 3 | 2022-11-30 | Wednesday |  | Logo 1st drawing digital | Package/Plan page DAY 1
| 3 | 2022-12-01 | Thursday | Feedback & changes on Logo after 1st drawing | Logo 2nd Drawing digital | " " DAY 2
| 3 | 2022-12-02 | Friday | Team Meeting | Team Meeting | Body Type & Health/ Diet Guide page DAY 1 & Team Meeting | Team Meeting
|  | 2022-12-03 | Saturday
|  | 2022-12-04 | Sunday
| 4 | 2022-12-05 | Monday | Feedback & changes on Logo after 2nd Drawing |  | " " DAY 2
| 4 | 2022-12-06 | Tuesday | Sprint Meeting | Logo Final | Blog page DAY 1
| 4 | 2022-12-07 | Wednesday |  |  | " " DAY 2
| 4 | 2022-12-08 | Thursday |  |  | Our partners page creation DAY 1
| 4 | 2022-12-09 | Friday | Team Meeting | Applying Final Changes & handing over logo to development team & Team Meeting | " " DAY 2 & Team Meeting | Team Meeting
|  | 2022-12-10 | Saturday
|  | 2022-12-11 | Sunday
Sprint 3 | 5 | 2022-12-12 | Monday | Sprint Meeting for 3rd sprint |  | Diet Surveypage creation DAY 1 | Testing for products creating on first 2 sprint DAY 1
| 5 | 2022-12-13 | Tuesday |  |  | " " DAY 2 | " " DAY 2
| 5 | 2022-12-14 | Wednesday |  |  | FAQ Page Creation DAY 1
| 5 | 2022-12-15 | Thursday |  |  | " " DAY 2 | Testing review for sprint 2 submission
| 5 | 2022-12-16 | Friday | Team Meeting | Team Meeting | Implementing changes from sprint 2 testing & feedback from client DAY 1 & Team Meeting | Team Meeting
|  | 2022-12-17 | Saturday
|  | 2022-12-18 | Sunday
| 6 | 2022-12-19 | Monday | Customer feedback for product until sprint 2 |  | Implementing logo on website
| 6 | 2022-12-20 | Tuesday | Sprint Meeting |  | Implementing customer feedback until sprint 2 on sites
| 6 | 2022-12-21 | Wednesday |  |  | Admin Portal Creations DAY 1
| 6 | 2022-12-22 | Thursday |  |  | " " DAY 2
| 6 | 2022-12-23 | Friday | Team Meeting | Team Meeting | " " DAY 3 Team Meeting | Team Meeting
|  | 2022-12-24 | Saturday
|  | 2022-12-25 | Sunday
Sprint 4 | 7 | 2022-12-26 | Monday | Sprint meet for 4th sprint |  | " " DAY 4 | Testing for products created on first 3 sprint
| 7 | 2022-12-27 | Tuesday |  |  | " " DAY 5 | " " DAY 2
| 7 | 2022-12-28 | Wednesday |  |  | Implementing changes from sprint 3 testing
| 7 | 2022-12-29 | Thursday | Team Meeting | Team Meeting | Team Meeting | Testing review for sprint 3 submission & Team Meeting
| 7 | 2022-12-30 | Friday | Feedback & Changes on pages created on sprint 2 from client, Sprint meet 2
|  | 2022-12-31 | Saturday
|  | 2023-01-01 | Sunday
| 8 | 2023-01-02 | Monday | Sprint Meeting |  | Customer feedback implementation
| 8 | 2023-01-03 | Tuesday |  |  | Website hosting & database setup, live website
| 8 | 2023-01-04 | Wednesday |  |  |  | Full website testing DAY 1
| 8 | 2023-01-05 | Thursday |  |  |  | " " DAY 2
| 8 | 2023-01-06 | Friday | Team Meeting | Team Meeting | Team Meeting | Testing review for full testing & Team Meeting
|  | 2023-01-07 | Saturday
|  | 2023-01-08 | Sunday
| 9 | 2023-01-09 | Monday | Customer testing the Website prototype for features & getting feedback |  | Implementing changes and fixing bugs from full testing.
|  | 2023-01-10 | Tuesday |  |  | Making changes on customer feedback and monitoring the website